PM1: Requirements Analysis and Modeling Report

University Trips & Events Management System

1. Project Information

Project Title

University Trips & Events Management System (UTEMS)

Team Members

| Name | Student ID | Role | Email |
| --- | --- | --- | --- |
| [Member 1 Name] | [ID] | Project Manager / Full Stack Developer | [email] |
| [Member 2 Name] | [ID] | Backend Developer / Database Designer | [email] |
| [Member 3 Name] | [ID] | Frontend Developer / UI/UX Designer | [email] |
| [Member 4 Name] | [ID] | QA Engineer / Documentation Lead | [email] |

Academic Information

- Course: CSE352 - Systems Analysis & Design

- Semester: [Current Semester]

- Submission Date: [Date]

- Instructor: [Instructor Name]

2. Project Description

Executive Summary

The University Trips & Events Management System (UTEMS) is a comprehensive digital platform designed to streamline the organization, management, and participation in university trips and events. The system addresses critical challenges in manual registration processes, capacity management, payment handling, and real-time communication between organizers and students.

Problem Statement

Currently, university event management faces several significant challenges:

- Manual Registration Burden: Students must physically visit offices or fill paper forms, leading to time waste and errors

- Capacity Control Issues: No automated system exists to prevent overbooking or track available seats in real-time

- Payment Complications: Cash-based transactions create delays, tracking difficulties, and require physical presence

- Communication Gaps: Students miss critical updates about timing, location changes, or cancellations

- Information Fragmentation: Event information is scattered across posters, social media, and word-of-mouth

- Ticketing Inefficiencies: Paper-based or list-based systems create fraud risks and entry confusion

- Limited Analytics: No data-driven insights for planning future events or measuring success

- Manual Workload: Organizers manually track attendance, payments, and capacity with high error risk

Solution Overview

UTEMS provides an integrated digital ecosystem featuring:

- Centralized Platform: Single point of access for all university events and trips

- Automated Workflows: Streamlined booking, payment, and ticketing processes

- Real-time Updates: Instant notifications for any event changes or updates

- Digital Ticketing: QR code-based tickets for secure, fraud-resistant entry

- Capacity Management: Automated seat tracking and booking prevention

- Payment Integration: Secure online payment processing with transaction tracking

- Analytics Dashboard: Comprehensive reporting for data-driven decision making

- Role-based Access: Separate interfaces and permissions for students, organizers, and administrators

Target Users

Students (Primary Users)

- Browse and discover upcoming events and trips

- Register and pay online

- Receive digital tickets and notifications

- Track booking history

Organizers (Content Managers)

- Create and manage events

- Monitor bookings and capacity

- Communicate with participants

- Access event-specific analytics

Administrators (System Managers)

- Oversee all system operations

- Manage users and permissions

- Generate comprehensive reports

- Monitor system performance

Expected Benefits

For Students:

- Convenient 24/7 access to event information

- Quick online registration and payment

- Immediate ticket delivery

- Timely notifications about updates

For Organizers:

- Reduced administrative workload

- Automated capacity management

- Easy participant communication

- Performance metrics access

For University:

- Improved operational efficiency

- Better financial tracking and transparency

- Enhanced student engagement

- Data-driven event planning

Technical Stack

- Frontend: Next.js with TypeScript, Tailwind CSS

- Backend: Nest.js with TypeScript

- Database: MongoDB with Mongoose ODM

- Authentication: JWT tokens

- Deployment: Docker containerization

- Development Tools: Git/GitHub, Postman, MongoDB Compass, PlantUML

3. High-Level Functional Requirements

FR1: User Authentication & Management

- FR1.1: User registration with university email verification

- FR1.2: Secure login with email and password

- FR1.3: Role-based access control (Student, Organizer, Administrator)

- FR1.4: Password reset functionality

- FR1.5: Account lockout after failed login attempts

- FR1.6: User profile management (view, edit, delete)

- FR1.7: Session management with JWT tokens

FR2: Event & Trip Management

- FR2.1: Create events with comprehensive details (name, description, date, time, location, capacity, price, category)

- FR2.2: Edit existing event information

- FR2.3: Delete/cancel events with automatic refund processing

- FR2.4: Display searchable event list to students

- FR2.5: Real-time capacity tracking and seat availability

- FR2.6: Set registration deadlines

- FR2.7: Categorize events (field trips, seminars, conferences, concerts)

- FR2.8: Upload and manage event images

FR3: Booking & Ticketing System

- FR3.1: Browse and search available events

- FR3.2: Reserve seats with availability verification

- FR3.3: Prevent duplicate bookings

- FR3.4: Generate unique QR code tickets

- FR3.5: Deliver digital tickets via email

- FR3.6: View booking history

- FR3.7: Cancel bookings with refund processing

- FR3.8: Validate QR codes at event entry

- FR3.9: Download tickets as PDF

FR4: Payment Processing

- FR4.1: Process online payments securely

- FR4.2: Verify payment confirmation

- FR4.3: Generate invoices/receipts

- FR4.4: Send payment confirmation notifications

- FR4.5: Handle refund transactions

- FR4.6: Track revenue per event

- FR4.7: Support multiple payment methods

FR5: System Administration

- FR7.1: Manage user accounts (activate, deactivate, delete)

- FR7.2: Assign and modify user roles

- FR7.3: Monitor system logs and security events

- FR7.4: Configure system settings

- FR7.5: Manage organizer permissions

- FR7.6: Audit financial transactions

4. Use Case Diagram

5. User Stories

Epic 1: User Authentication & Account Management

US1.1: Student Registration

- As a student

- I want to register for an account using my university email

- So that I can access the event management system

- Acceptance Criteria:

  - Registration form includes: first name, last name, university email, phone, faculty, academic year, password

  - Password must meet strength requirements (min 8 chars, uppercase, lowercase, number, special char)

  - System sends email verification link

  - Account is inactive until email is verified

  - System prevents duplicate email registrations

- Priority: High

- Story Points: 5

US1.2: User Login

- As a registered user

- I want to log in with my credentials

- So that I can access my personalized dashboard

- Acceptance Criteria:

  - Login with email and password

  - System validates credentials

  - Account locks after 5 failed attempts

  - Redirect to role-appropriate dashboard

  - Session maintained with JWT token

- Priority: High

- Story Points: 3

US1.3: Password Reset

- As a user who forgot my password

- I want to reset my password via email

- So that I can regain access to my account

- Acceptance Criteria:

  - "Forgot Password" link available on login page

  - System sends reset link to registered email

  - Reset link expires after 30 minutes

  - User can set new password meeting strength requirements

  - Confirmation email sent after successful reset

- Priority: Medium

- Story Points: 3

US1.4: Profile Management

- As a logged-in user

- I want to view and edit my profile information

- So that I can keep my details up to date

- Acceptance Criteria:

  - View current profile information

  - Edit name, phone number, faculty, academic year

  - Cannot change email address

  - Changes saved successfully

  - Confirmation message displayed

- Priority: Low

- Story Points: 2

Epic 2: Event Discovery & Management

US2.1: Browse Events

- As a student

- I want to browse all available events

- So that I can discover interesting activities

- Acceptance Criteria:

  - Display list of upcoming events

  - Show event name, date, location, price, available seats

  - Events sorted by date (nearest first)

  - Pagination for large lists

  - Clear indication of full events

- Priority: High

- Story Points: 3

US2.2: Search and Filter Events

- As a student

- I want to search and filter events

- So that I can quickly find events that interest me

- Acceptance Criteria:

  - Search by event name or description

  - Filter by category (trips, seminars, conferences, concerts)

  - Filter by date range

  - Filter by price range

  - Filter by availability

  - Search results update in real-time

- Priority: Medium

- Story Points: 5

US2.3: View Event Details

- As a student

- I want to view detailed information about an event

- So that I can decide whether to book it

- Acceptance Criteria:

  - Display full event description

  - Show date, time, location, price

  - Display available seats count

  - Show registration deadline

  - Display event category

  - Show event image (if available)

  - "Book Now" button visible if seats available

- Priority: High

- Story Points: 3

US2.4: Create Event

- As an organizer

- I want to create a new event

- So that students can discover and register for it

- Acceptance Criteria:

  - Form includes all required fields (name, description, date, time, location, capacity, price, category)

  - Optional event image upload

  - Set registration deadline

  - Validate all inputs (no past dates, positive capacity, valid price)

  - Event saved to database

  - Event immediately visible to students

  - Confirmation message displayed

- Priority: High

- Story Points: 8

US2.5: Edit Event

- As an organizer

- I want to edit existing event details

- So that I can update information or fix errors

- Acceptance Criteria:

  - Load existing event data into form

  - Allow modification of all fields except bookings count

  - Validate changes

  - Update database

  - Send notification to registered students

  - Cannot reduce capacity below current bookings

  - Success message displayed

- Priority: High

- Story Points: 5

US2.6: Delete/Cancel Event

- As an organizer

- I want to cancel an event

- So that students know it won't occur and receive refunds

- Acceptance Criteria:

  - Confirmation dialog before deletion

  - Check for existing bookings

  - Process refunds for all bookings

  - Send cancellation notifications

  - Remove event from active listings

  - Maintain record for reporting purposes

- Priority: Medium

- Story Points: 5

Epic 3: Booking & Ticketing

US3.1: Book Event

- As a student

- I want to book a seat for an event

- So that I can attend it

- Acceptance Criteria:

  - Check seat availability before booking

  - Prevent duplicate bookings for same event

  - Verify registration deadline not passed

  - Create booking record

  - Redirect to payment

  - Display booking summary

- Priority: High

- Story Points: 8

US3.2: View Booking History

- As a student

- I want to view my past and upcoming bookings

- So that I can track my event participation

- Acceptance Criteria:

  - Display all bookings (past and future)

  - Show event name, date, booking status

  - Filter by status (upcoming, past, cancelled)

  - Access tickets for upcoming events

  - View payment receipts

- Priority: Medium

- Story Points: 3

US3.3: Cancel Booking

- As a student

- I want to cancel my booking

- So that I can get a refund if I can't attend

- Acceptance Criteria:

  - Select booking to cancel

  - Check cancellation policy/deadline

  - Confirmation dialog

  - Process refund

  - Free up seat for other students

  - Send cancellation confirmation email

  - Update booking status to cancelled

- Priority: Medium

- Story Points: 5

US3.4: Generate and Receive QR Ticket

- As a student who completed payment

- I want to receive a QR code ticket

- So that I can use it for event entry

- Acceptance Criteria:

  - Generate unique QR code upon payment success

  - QR code contains booking ID and validation data

  - Send ticket via email immediately

  - Include event details in email

  - Allow ticket download as PDF

  - QR code clearly visible and scannable

- Priority: High

- Story Points: 5

US3.5: Validate Ticket at Entry

- As an organizer

- I want to scan and validate QR tickets

- So that I can verify attendees and prevent fraud

- Acceptance Criteria:

  - Scan QR code using mobile device or scanner

  - Validate ticket against database

  - Display booking details (student name, event)

  - Mark ticket as used (prevent reuse)

  - Show validation result (valid/invalid/already used)

  - Track attendance in real-time

- Priority: High

- Story Points: 5

Epic 4: Payment Processing

US4.1: Process Online Payment

- As a student

- I want to pay for my booking online

- So that I can complete my registration conveniently

- Acceptance Criteria:

  - Secure payment form displayed

  - Support multiple payment methods

  - Validate payment details

  - Process payment through gateway

  - Handle payment success/failure

  - Transaction completes within 5 seconds

  - Display confirmation or error message

- Priority: High

- Story Points: 8

US4.2: Receive Payment Confirmation

- As a student who completed payment

- I want to receive payment confirmation

- So that I have proof of payment

- Acceptance Criteria:

  - Send email confirmation immediately

  - Include transaction details

  - Include digital invoice/receipt

  - Display payment status on dashboard

  - Store transaction record

- Priority: Medium

- Story Points: 3

US4.3: Process Refund

- As a student with cancelled booking

- I want to receive my refund

- So that I get my money back

- Acceptance Criteria:

  - Automatic refund processing on cancellation

  - Refund to original payment method

  - Send refund confirmation email

  - Update payment status

  - Process within 3-5 business days

- Priority: Medium

- Story Points: 5

Epic 5: Notifications & Communication

US5.1: Receive Event Notifications

- As a student

- I want to receive notifications about new events

- So that I don't miss interesting opportunities

- Acceptance Criteria:

  - Email sent when new event is created

  - Include event details and link

  - Filter by student preferences (future enhancement)

  - Notification delivered within 1 minute

- Priority: Medium

- Story Points: 3

US5.2: Receive Event Updates

- As a registered student

- I want to receive notifications about event changes

- So that I stay informed about updates

- Acceptance Criteria:

  - Email sent when event details change

  - Include old and new information

  - Clear indication of what changed

  - Link to updated event details

- Priority: High

- Story Points: 3

US5.3: Receive Event Reminders

- As a registered student

- I want to receive reminder before the event

- So that I don't forget to attend

- Acceptance Criteria:

  - Reminder sent 24 hours before event

  - Include event details and ticket

  - Include QR code for easy access

  - Option to add to calendar

- Priority: Medium

- Story Points: 3

US5.4: Send Custom Messages to Participants

- As an organizer

- I want to send messages to all registered participants

- So that I can communicate important information

- Acceptance Criteria:

  - Message composition interface

  - Send to all registered students for specific event

  - Preview before sending

  - Confirmation of successful delivery

  - Message log maintained

- Priority: Low

- Story Points: 3

Epic 6: Reporting & Analytics

US6.1: View Analytics Dashboard

- As an organizer/administrator

- I want to view an analytics dashboard

- So that I can monitor system performance

- Acceptance Criteria:

  - Display total registered users

  - Show active events count

  - Display total bookings

  - Show total revenue

  - Display popular event categories

  - Real-time data updates

  - Visual charts and graphs

- Priority: Medium

- Story Points: 5

US6.2: Generate Participant Report

- As an organizer

- I want to see participant statistics

- So that I can understand event popularity

- Acceptance Criteria:

  - Show participant count per event

  - Display capacity utilization percentage

  - Filter by date range

  - Filter by event category

  - Export as PDF/CSV

- Priority: Medium

- Story Points: 5

US6.3: Generate Revenue Report

- As an administrator

- I want to view revenue reports

- So that I can track financial performance

- Acceptance Criteria:

  - Display total revenue

  - Show revenue per event

  - Revenue trends over time

  - Revenue by category

  - Payment method breakdown

  - Export capability

- Priority: Medium

- Story Points: 5

US6.4: Generate Attendance Report

- As an organizer

- I want to track actual attendance

- So that I can measure event success

- Acceptance Criteria:

  - Show tickets validated (QR scans)

  - Calculate attendance rate

  - Display no-show rate

  - Compare with booking count

  - Export attendee list

- Priority: Low

- Story Points: 3

Epic 7: System Administration

US7.1: Manage User Accounts

- As an administrator

- I want to manage user accounts

- So that I can maintain system integrity

- Acceptance Criteria:

  - View all user accounts

  - Search and filter users

  - Activate/deactivate accounts

  - Delete accounts

  - View user activity logs

  - Unlock locked accounts

- Priority: Medium

- Story Points: 5

US7.2: Manage Permissions

- As an administrator

- I want to assign and modify user roles

- So that I can control access levels

- Acceptance Criteria:

  - View current user role

  - Assign role (Student, Organizer, Administrator)

  - Change existing roles

  - Confirmation required for role changes

  - Audit log of role changes

- Priority: Low

- Story Points: 3

US7.3: View System Logs

- As an administrator

- I want to view system logs and security events

- So that I can monitor for issues and security threats

- Acceptance Criteria:

  - Display authentication logs

  - Show system errors

  - Display security events

  - Filter by date range

  - Filter by event type

  - Export logs

- Priority: Low

- Story Points: 3

6. Estimation Computation & Gantt Chart

Estimation Methodology

Based on the lecture content, we'll use a combination of approaches:

- Story Points to Hours Conversion: 1 Story Point = 4 hours of development time

- Team Velocity: Assuming 40 hours/week per developer, 4 developers = 160 hours/week team capacity

- Buffer Time: Adding 20% contingency for unexpected issues

- Phases: Following RAD principles with iterative development

User Story Estimation Summary

| Epic | User Story | Story Points | Hours | Dependencies |
| --- | --- | --- | --- | --- |
| Epic 1: Authentication |  | 16 SP | 64 hrs |  |
|  | US1.1: Student Registration | 5 | 20 | - |
|  | US1.2: User Login | 3 | 12 | US1.1 |
|  | US1.3: Password Reset | 3 | 12 | US1.2 |
|  | US1.4: Profile Management | 2 | 8 | US1.2 |
|  | Setup & Infrastructure | 3 | 12 | - |
| Epic 2: Event Management |  | 29 SP | 116 hrs |  |
|  | US2.1: Browse Events | 3 | 12 | US1.2 |
|  | US2.2: Search and Filter | 5 | 20 | US2.1 |
|  | US2.3: View Event Details | 3 | 12 | US2.1 |
|  | US2.4: Create Event | 8 | 32 | US1.2 |
|  | US2.5: Edit Event | 5 | 20 | US2.4 |
|  | US2.6: Delete Event | 5 | 20 | US2.4 |
| Epic 3: Booking & Ticketing |  | 26 SP | 104 hrs |  |
|  | US3.1: Book Event | 8 | 32 | US2.3 |
|  | US3.2: View Booking History | 3 | 12 | US3.1 |
|  | US3.3: Cancel Booking | 5 | 20 | US3.1 |
|  | US3.4: Generate QR Ticket | 5 | 20 | US4.1 |
|  | US3.5: Validate Ticket | 5 | 20 | US3.4 |
|  | US4.3: Process Refund | 5 | 20 | US4.1 |
| Epic 5: Notifications |  | 12 SP | 48 hrs |  |
|  | US5.1: Event Notifications | 3 | 12 | US2.4 |
|  | US5.2: Event Updates | 3 | 12 | US2.5 |
|  | US5.3: Event Reminders | 3 | 12 | US3.1 |
|  | US5.4: Custom Messages | 3 | 12 | US2.4 |
| Epic 6: Reporting |  | 18 SP | 72 hrs |  |
|  | US6.1: Analytics Dashboard | 5 | 20 | US3.1 |
|  | US6.2: Participant Report | 5 | 20 | US6.1 |
|  | US6.3: Revenue Report | 5 | 20 | US6.1 |
|  | US6.4: Attendance Report | 3 | 12 | US3.5 |
| Testing & QA |  | 16 SP | 64 hrs |  |
|  | Integration Testing | 8 | 32 | All features |
|  | User Acceptance Testing | 5 | 20 | All features |
|  | Bug Fixes & Polish | 3 | 12 | Testing |
| Deployment |  | 5 SP | 20 hrs |  |
|  | Production Setup | 3 | 12 | All features |
|  | Documentation | 2 | 8 | All features |
| TOTAL |  | 149 SP | 596 hrs |  |

Time Estimation with Buffer

Base Development Time: 596 hours

Buffer (20%): 119 hours

Total Estimated Time: 715 hours

Team Distribution

With 4 developers working 40 hours/week:

- Weekly Team Capacity: 160 hours

- Estimated Duration: 715 ÷ 160 = 4.5 weeks ≈ 5 weeks

Sprint Planning (2-week sprints)

Sprint 1 (Weeks 1-2): Foundation

- Project setup & infrastructure

- Authentication system

- Basic user management

- Database schema design

Sprint 2 (Weeks 3-4): Core Features

- Event management (CRUD)

- Booking system

- Payment integration

- Basic notifications

Sprint 3 (Weeks 5-6): Advanced Features

- QR ticketing system

- Advanced notifications

- Reporting & analytics

- Admin panel

Sprint 4 (Weeks 7-8): Polish & Testing

- Integration testing

- UAT

- Bug fixes

- Documentation

- Deployment

Gantt Chart

Critical Path Analysis

Critical Path (Longest dependency chain):

- Project Setup → Authentication → Event Management → Booking → Payment → QR Tickets → Testing → Deployment

Critical Activities:

- Authentication System (foundational for all features)

- Event Management (required for booking)

- Payment Integration (required for booking completion)

- QR Ticket Generation (required for entry validation)

Risk Mitigation:

- Start critical path activities early

- Parallel development where possible (notifications, reports)

- Buffer time allocated for each sprint

- Daily standups to catch delays early

Resource Allocation

| Developer | Primary Focus | Secondary Focus |
| --- | --- | --- |
| Developer 1 | Backend (Auth, Events) | Database Design |
| Developer 2 | Backend (Booking, Payment) | API Integration |
| Developer 3 | Frontend (UI/UX) | Testing |
| Developer 4 | Full Stack (Reports, Admin) | DevOps/Deployment |

7. Initial SOLID-Based Class Diagram

Architecture Overview

The system follows a layered architecture with clear separation of concerns:

- Presentation Layer: Next.js components (not shown in backend diagram)

- API Layer: Controllers handling HTTP requests

- Business Logic Layer: Services implementing business rules

- Data Access Layer: Repositories for database operations

- Domain Layer: Entities representing business concepts

SOLID Principles Applied

S - Single Responsibility Principle

- Each class has one specific responsibility

- Controllers handle HTTP, Services handle business logic, Repositories handle data access

O - Open/Closed Principle

- Use of interfaces allows extension without modification

- Strategy pattern for payment processing

L - Liskov Substitution Principle

- All implementations can substitute their interfaces

- User types (Student, Organizer, Admin) all implement IUser

I - Interface Segregation Principle

- Multiple specific interfaces rather than one large interface

- Clients depend only on interfaces they use

D - Dependency Inversion Principle

- High-level modules depend on abstractions (interfaces)

- Dependency injection used throughout

Project Estimation Using Fibonacci Method - University Trips & Events Management System (UTEMS)

CSE352: Systems Analysis & Design - Milestone 3

1. Use Case Listing (5 Sprints)

Based on core functionality requirements:

- Manage authentication

- Manage user profiles

- Manage events

- Manage bookings

- Manage payments

- Manage QR ticketing

- Manage notifications

- Manage analytics & reporting

- Manage user roles & permissions

- Manage event categories

- Manage refunds

- Manage event search & filters

- Manage booking history

- Manage system administration

- Manage email verification

2. Fibonacci Estimation Method

2.1 Estimation Principles

Using the Fibonacci sequence for story point estimation:

- 1 point: Very simple task (1-2 hours)

- 2 points: Simple task (2-4 hours)

- 3 points: Moderate task (4-8 hours)

- 5 points: Complex task (8-16 hours / 1-2 days)

- 8 points: Very complex task (16-24 hours / 2-3 days)

- 13 points: Highly complex task (24-40 hours / 3-5 days)

2.2 Assumptions

- Team Size: 4 developers

- Working Hours: 8 hours per day

- Work Days: 5 days per week

- Sprint Duration: 2 weeks

- Velocity: 35 story points per sprint (per team)

3. Detailed Use Case Estimation by Sprint

Sprint 1: Foundation - Authentication & User Management

| Use Case | Story Points | Effort (Hours) | Duration (Days) | Dependencies |
| --- | --- | --- | --- | --- |
| Manage authentication | 8 | 24 | 3 | None |
| Manage user profiles | 5 | 15 | 2 | Manage authentication |
| Manage email verification | 5 | 15 | 2 | Manage authentication |
| Manage user roles & permissions | 5 | 15 | 2 | Manage authentication |

Sprint 1 Subtotal: 23 points, 69 hours, ~9 days

Tasks Breakdown:

| Task | Duration (Hours) |
| --- | --- |
| User registration with university email | 6 |
| Email verification system | 5 |
| Login/Logout with JWT | 8 |
| Password reset mechanism | 5 |
| Account lockout after 5 failed attempts | 4 |
| Profile CRUD operations | 8 |
| Profile image upload | 4 |
| Role-based access control (Student/Organizer/Admin) | 10 |
| Session management with JWT tokens | 6 |
| User dashboard by role | 7 |
| Account activation system | 6 |

Sprint 2: Core Event Management

| Use Case | Story Points | Effort (Hours) | Duration (Days) | Dependencies |
| --- | --- | --- | --- | --- |
| Manage events | 13 | 40 | 5 | Manage authentication |
| Manage event categories | 3 | 9 | 1 | Manage events |
| Manage event search & filters | 8 | 24 | 3 | Manage events |

Sprint 2 Subtotal: 24 points, 73 hours, ~9 days

Tasks Breakdown:

| Task | Duration (Hours) |
| --- | --- |
| Event creation form (all fields) | 8 |
| Event validation (dates, capacity, price) | 5 |
| Event image upload and management | 4 |
| Event editing with student notifications | 8 |
| Event deletion with refund processing | 6 |
| Real-time capacity tracking | 5 |
| Registration deadline management | 4 |
| Event categorization system | 5 |
| Search by name/description | 6 |
| Filter by category | 4 |
| Filter by date range | 4 |
| Filter by price range | 4 |
| Filter by availability | 4 |
| Event list with pagination | 6 |

Sprint 3: Booking & Payment System

| Use Case | Story Points | Effort (Hours) | Duration (Days) | Dependencies |
| --- | --- | --- | --- | --- |
| Manage bookings | 13 | 40 | 5 | Manage events |
| Manage payments | 13 | 40 | 5 | Manage bookings |
| Manage booking history | 3 | 9 | 1 | Manage bookings |

Sprint 3 Subtotal: 29 points, 89 hours, ~11 days

Tasks Breakdown:

| Task | Duration (Hours) |
| --- | --- |
| Booking creation interface | 6 |
| Seat availability verification | 5 |
| Duplicate booking prevention | 4 |
| Registration deadline check | 3 |
| Booking summary page | 4 |
| Payment gateway integration | 10 |
| Multiple payment methods support | 8 |
| Payment validation | 5 |
| Transaction processing | 6 |
| Payment success/failure handling | 5 |
| Invoice/receipt generation | 6 |
| Revenue tracking per event | 5 |
| Booking history display | 5 |
| Filter by booking status | 4 |
| Access to payment receipts | 4 |
| Booking cancellation interface | 5 |
| Cancellation deadline check | 4 |

Sprint 4: QR Ticketing & Notifications

| Use Case | Story Points | Effort (Hours) | Duration (Days) | Dependencies |
| --- | --- | --- | --- | --- |
| Manage QR ticketing | 13 | 40 | 5 | Manage payments |
| Manage refunds | 8 | 24 | 3 | Manage payments |
| Manage notifications | 8 | 24 | 3 | Manage events |

Sprint 4 Subtotal: 29 points, 88 hours, ~11 days

Tasks Breakdown:

| Task | Duration (Hours) |
| --- | --- |
| QR code generation upon payment | 8 |
| Unique QR code with booking validation data | 6 |
| QR ticket email delivery | 5 |
| Ticket PDF generation | 6 |
| QR code scanning interface | 5 |
| Ticket validation against database | 6 |
| Mark ticket as used (prevent reuse) | 4 |
| Real-time attendance tracking | 5 |
| Display validation result | 3 |
| Automated refund processing | 8 |
| Refund to original payment method | 6 |
| Refund confirmation email | 4 |
| Refund status tracking | 6 |
| New event announcement emails | 4 |
| Event update notifications | 5 |
| Event cancellation notifications | 4 |
| Payment confirmation emails | 4 |
| 24-hour event reminders | 5 |
| Custom organizer messages | 4 |

Sprint 5: Analytics, Reporting & Administration

| Use Case | Story Points | Effort (Hours) | Duration (Days) | Dependencies |
| --- | --- | --- | --- | --- |
| Manage analytics & reporting | 13 | 40 | 5 | All previous features |
| Manage system administration | 8 | 24 | 3 | Manage authentication |

Sprint 5 Subtotal: 21 points, 64 hours, ~8 days

Tasks Breakdown:

| Task | Duration (Hours) |
| --- | --- |
| Analytics dashboard design | 6 |
| Total registered users metric | 3 |
| Active events count | 3 |
| Total bookings metric | 3 |
| Total revenue display | 4 |
| Popular event categories chart | 5 |
| Real-time data updates | 4 |
| Participant count report | 5 |
| Capacity utilization calculation | 4 |
| Revenue report per event | 5 |
| Revenue trends over time | 5 |
| Attendance tracking report | 4 |
| Export reports (PDF/CSV) | 5 |
| User account management interface | 6 |
| Search and filter users | 4 |
| Activate/deactivate accounts | 3 |
| Delete user accounts | 3 |
| Role assignment system | 4 |
| System logs and security events | 5 |
| Unlock locked accounts | 3 |

4. Total Project Estimation Summary

4.1 Overall Statistics

| Metric | Value |
| --- | --- |
| Total Story Points | 126 |
| Total Effort (Person-Hours) | 383 |
| Total Duration (Calendar Days) | 48 days (~10 weeks) |
| Number of Sprints | 5 sprints × 2 weeks = 10 weeks |
| With Testing & Integration | +3 weeks |
| Total Project Duration | 13 weeks (3.25 months) |

4.2 Phase Breakdown

| Phase | Duration | Activities |
| --- | --- | --- |
| Sprint 1 | 2 weeks | Authentication, profiles, email verification, roles |
| Sprint 2 | 2 weeks | Event management, categories, search & filters |
| Sprint 3 | 2 weeks | Booking system, payment processing, booking history |
| Sprint 4 | 2 weeks | QR ticketing, refunds, notifications |
| Sprint 5 | 2 weeks | Analytics, reporting, system administration |
| Integration & Testing | 2 weeks | System testing, bug fixes, performance optimization |
| Deployment & UAT | 1 week | User acceptance testing, production deployment |

5. Resource Allocation

5.1 Team Composition

| Role | Number | Responsibility |
| --- | --- | --- |
| Backend Developers | 2 | API development, database design, business logic, payment integration |
| Frontend Developers | 1 | UI/UX implementation, Next.js components, client-side logic |
| Full-Stack Developer | 1 | QR system, complex integrations, DevOps, deployment |
| QA Engineer | 1 | Testing, quality assurance (part-time) |
| Project Manager | 1 | Coordination, planning, stakeholder communication (part-time) |

5.2 Developer Assignment by Sprint

| Developer | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 |
| --- | --- | --- | --- | --- | --- |
| Developer 1 (Backend) | Auth, JWT | Event CRUD | Booking API | Refund logic | Reports API |
| Developer 2 (Backend) | Email system | Search/Filter | Payment gateway | Notification service | Admin API |
| Developer 3 (Frontend) | Login/Register UI | Event pages | Booking UI | Ticket display | Dashboard UI |
| Developer 4 (Full-Stack) | Role system | Categories | Payment UI | QR generation/scan | Analytics charts |

6. Milestones & Deliverables

| Milestone | Week | Deliverable |
| --- | --- | --- |
| M1: Foundation Complete | Week 2 | Authentication, profiles, email verification, role system |
| M2: Event System Ready | Week 4 | Event management, search, filters, categories |
| M3: Core Transactions | Week 6 | Booking and payment system functional |
| M4: Advanced Features | Week 8 | QR ticketing, refunds, notifications working |
| M5: Full Feature Set | Week 10 | Analytics, reporting, admin panel complete |
| M6: System Ready | Week 12 | Integration testing complete, bug fixes done |
| M7: Go-Live | Week 13 | Production deployment, UAT passed |

7. Sprint Schedule (13 weeks total)

Week 1-2:  ████████ Sprint 1: Authentication & User Management

Week 3-4:  ████████ Sprint 2: Event Management

Week 5-6:  ████████ Sprint 3: Booking & Payment

Week 7-8:  ████████ Sprint 4: QR Ticketing & Notifications

Week 9-10: ████████ Sprint 5: Analytics & Administration

Week 11-12: ████████ Integration & System Testing

Week 13:   ████████ Deployment & UAT